**Kitt Peak 600k Task List**

1. RWGPS: <https://ridewithgps.com/routes/31434149>
2. Cue sheet: <http://www.azbrevet.com/assets/cuesheets/KittPeak600k.pdf>
3. Pre ride report:
4. Pre event:
	1. Print Brevet cards, cue sheets and Waivers - **Mike**
	2. Last minute notes to riders - **Mike**
	3. Make roster w/Controls for riders tracking - **Mike**
	4. Buy/make food – **Steve**
5. La Quinta Start 05:00-06:00: **Steve/Carlton TBD**
	1. Use breakfast room as gathering place.
	2. Rider check-in at 4:30
	3. Distribute Brevet cards/Cue sheets after signing waiver
	4. Coffee/Water – supplied by La Quinta
	5. Pastry, Bananas
6. 3 Points store NOT A CONTROL, convenience only for outbound riders, set up near bathrooms: **Carlton**
	1. Water, Bananas, snacks, muffins
7. Kitt Peak – Steve
	1. Water, bananas, snacks, muffins
8. Sells 9:39-15.32: **Carlton** –Bashas/Tohono Plaza Parking lot.
	1. Lunch provided. Costco wraps, set up at the tables, that will be less places for riders to go.
	2. Soda, Water, Chips, Snacks, Bananas
	3. Other options, Bashas, Desert Rain Cafe
9. Arivaca 13:42-00:20: Carlton **Water stash at Arivaca Mercantile if necessary**
	1. Lunch for early riders,
	2. Snacks/leftovers for late riders:
		1. Arivaca
			1. Mercantile is open to 1700
		2. We will know what time the last rider leaves Rio Rico. If they are later than 18:00, Brian will have support there with water/snacks. Carlton returns to the La Quinta after last rider leaves Arivaca, or the control closes.
10. Green Valley – No support
11. La Quinta Inn (400k distance) 17:38-08:40 next day
	1. Dinner/Breakfast all night long – **Steve with Carlton joining after Arivaca closes/last rider**
		1. Mike: you mentioned we would use the suite; will we have access to the breakfast area as well?
12. San Manuel 19:34-12:30 next day – **Steve/Carlton**
	1. Steve will leave depending on timing of riders leaving early, probably @ 0700
	2. If riders leave at 04:00, that would put them there @07:00, earliest. So support could be between 07:00-12:00.
	3. Water, bananas, snacks, encouragement!
13. Park Link & Marana – No support
14. Finish – No support
	1. Cards signed by Hotel staff and dropped in USPS envelope/box that Hotel will drop in the mail to Mike. Steve to procure postage and box/envelope, Mike, did this work well last year, we can do this again if it did.

STAFFING PLAN:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **INDEX** | **MILE** | **PLACE** | **Start** | **Close** | **STAFF (or vice versa )** |
| 5 | 0 | LaQuinta | 0500 | 0600 | Steve - Sweeps to 3 Points, Carlton leaps to 3 Pts |
| 6 | 37 | 3 Points | 0646 | 0900 | CVL – Sweeps to Kitt Peak, SWA leaps to Kitt Peak |
| 7 | 65 | Kitt Peak | 0805 | 1200 | SWA sets up snacks/water |
| 8 | 126 | Sells | 0939 | 1532 | CVL leaps to Sells and sets up lunch, SWA sweeps to Sells after last rider leaves Kitt peak |
| 9 | 163 | Arivaca | 1249 | 2228 | CVL leaps to Arivaca 1.5 hour drive SWA sweeps to Arivaca if riders are compact and well ahead of close times, SWA leaps LaQuinta (1.5hr drive) depending on rider progress |
| 11 | 250 | LaQuinta | 1718 | 0840 Sun | BOTH share. If riders need assistance overnight, one can leave and backtrack to assist |
| 12 | 295 | San Manuel | 2020 | 1348 Sun | SWA Leaps to San Manuel with left-overs and heads home at the close. CVL either joins SWA at San Manuel or heads home |

Following food list to be updated:

